**Annex II**

|  |  |  |
| --- | --- | --- |
| NEW Master Program TENTATIVE task calendar | | |
| Date | Function | Status |
| February 2018 | Finalisation of the evaluation report and recommendations following the 1st EJMP | In progress |
| March | Launching a call for Experts |  |
| April | Selection of experts |  |
| May | Presentation of EJMP (1) evaluation and expert group constellation to MB |  |
| June | 1st expert group meeting Identifying chair, action plan and structure |  |
| September | 2nd meeting |  |
| November | 3rd meeting |  |
| February 2019 | 4th meeting |  |
| March/April | Report /documents |  |
| May | MB approval |  |
| June | Establishment of Consortium |  |
| July | Initiation of accreditation |  |
| March 2020 | ‘Steering Board’ approval of accreditation and selection of implementing Universities |  |
| April | Call for students |  |
| June | Selection of students by ‘Master Programme Committee’ |  |
| July-September | Development of Student guide |  |
| October | Start of Master Programme |  |